## Color
PROJECT: Color
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project start date: | 2022-10-10 |  |  |  |  | October | [27 empty] | November
Scrolling increment: | 0 | time axis 2022-10-10 to 2022-12-04
Milestone description | Category | Ranking | Progress | Start | Days | time axis 2022-10-10 to 2022-12-04
Grid-Based Building System | Goal |  | 100% | 2022-10-10 | 84 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Display Grid | On Track | Must | 100% | 2022-10-10 | 20
Place 'Buildings' On Grid | On Track | Must | 100% | 2022-10-20 | 18
Implement 'Building' Assets | On Track | Must | 100% | 2022-10-25 | 5
Rotate Buildings | On Track | Must | 100% | 2022-10-28 | 20
Economic Model and Display Outcome - Graph | Goal |  | 100% | 2023-01-01 | 111
Shifting In Graph | On Track | Must | 100% | 2023-01-20 | 20
Elasticity of Graph | On Track | Must | 100% | 2023-02-01 | 20
Grid Lines | On Track | Must | 100% | 2023-03-05 | 15
Data on graph |  | Should | 10% |  | 3
Display information on what caused the shifts of the curves |  | Should | 0% |  | 0
Economic agent behaviour changes based on graph |  | Should | 0% |  | 0
Random Events For Input | Med Risk | Must | 100% | 2023-04-01 | 24
Learning Resources | Goal |  | 100% | 2023-01-01 | 111
Interactive Graph | On Track | Must | 100% | 2023-03-01 | 4
Details on causes of shift | On Track | Must | 100% | 2023-04-01 | 24
Details on causes of elasticity | On Track | Must | 100% | 2023-04-01 | 24
Mobile Controls | Goal |  | 100% | 2023-01-01 | 111
Touch Input | Med Risk | Must | 100% | 2023-03-02 | 7
Background Research (Report / Study) | Goal |  | 100% | 2022-10-10 | 84 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Questionnaire | On Track | Must | 100% | 2022-10-10 | 40
Research Paper 1 | On Track | Must | 100% | 2022-10-10 | 20
Research Paper 2 | On Track | Must | 100% | 2022-10-24 | 22
Research Paper 3 | On Track | Must | 100% | 2022-11-11 | 24
Research Paper 4 | Low Risk | Must | 100% | 2022-12-08 | 24
Research Paper 5 | Med Risk | Must | 100% | 2022-12-22 | 24
Project Process and Management (Report) | Goal |  | 100% | 2023-03-01 | 111
Software Methodology | On Track | Must | 100% | 2023-03-21 | 15
Requirement Analysis | On Track | Must | 100% | 2023-03-21 | 20
Design | On Track | Must | 100% | 2023-03-21 | 3
Implementation | On Track | Must | 100% | 2023-04-01 | 15
Evaluation and Reflection (Report / Study) | Goal |  | 100% | 2023-03-01 | 111
Systematic Feedback | On Track | Must | 100% | 2023-03-10 | 13
Conclusion | On Track | Must | 100% | 2023-04-01 | 13
To add more data, Insert new rows ABOVE this one